## Lofthus frukt og saft
Project Methodology Technology - Course Assignment
Lofthus frukt og saft - Gantt Chart
The Tasks |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
Start Date: 27. 01. 2020 | End Date: 01.03.2020 |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
PLANNING
Plan design | A. Havsgård | 2 d | bar: WEEK 1 M to WEEK 1 T
Plan the content | T. Lunde | 2 d | bar: WEEK 1 W to WEEK 1 TH
Take photos | C. Mendes | 2 d | bar: WEEK 1 F to WEEK 1 SA
SITE DEVELOPMENT | bar: WEEK 1 SU
Gather info | Everyone | 2 d | bar: WEEK 2 M to WEEK 2 T
Planning | A. Havsgård | 1 d | bar: WEEK 2 W
Design | S. Kvåle | 3 d | bar: WEEK 2 TH to WEEK 2 SA
Development | A. Havsgård | 4 d | bar: WEEK 2 SA to WEEK 3 T
Test | A. Havsgård | 2 d | bar: WEEK 3 T to WEEK 3 W
Maintenance | A. Havsgård | 1 d | bar: WEEK 3 TH
CONTENT | bar: WEEK 3 F
Make Articles | T. Lunde | 3 d | bar: WEEK 3 SA to WEEK 4 M
Fix photos | C. Mendes | 2 d | bar: WEEK 4 T to WEEK 4 W
Coloring | Stian Kvåle | 3 d | bar: WEEK 4 W to WEEK 4 F
LAUNCHING | bar: WEEK 4 SA
Distribution Deals | A. Easton | 2 d | bar: WEEK 4 SU to WEEK 5 M
Marketing Push | D. Cardoso | 2 d | bar: WEEK 5 T to WEEK 5 W
Launch | A. Havsgård | 1 d | bar: WEEK 5 TH
Maintenance | A. Havsgård | 3 d | bar: WEEK 5 F to WEEK 5 SU
|  |  |  | Days it takes to do the task | [12 empty] | Lofthus frukt og saft - TEAM
CEO – Ari Easton
|  |  |  | Meeting for everyone in the comapny | [12 empty] | Chief Marketing Officer (CMO) – Divaldo Cardoso
Copywriter – Torgeir Lunde
|  |  |  | Days when different tasks overlap | [12 empty] | Photographer – Carlos Mendes
Front-end developer – Anders Havsgård
Designer – Stian Kvåle